## Gantt Chart (Dates)
Weekly Gantt Chart
Scavenger Robot Project: Welcome to Servo Buster
| Tasks | Start Date | End Date | Week 1 (Feb 8-15) | Week 2 (Feb 16-22) | Week 3 (Feb 23-Mar 1) | Week 4 (Mar 2-8) | Week 5 (Mar 9-15) | Week 6 (Mar 16-22) | Week 7 Mar 22-29) | Week 8 (Mar 30- Apr 5) | Week 9 (Mar Apr 6-9)
1 | Milestone 1
1.1 | Concept Generation | 2026-02-10 | 2026-02-13
1.2 | Concept Selection & Report | 2026-02-12 | 2026-02-13
2 | Milestone 2
2.1 | Mechanical design & CAD modeling (Chassis & Scoop) | 2026-02-17 | 2026-03-08
2.2 | CAD Design (Sorting System) | 2026-02-24 | 2026-03-08
2.3 | Bill Of Materials | 2026-03-02 | 2026-03-08
3 | Milestone 3
3.1 | Prototype Fabrication (Chassis & Scoop 3D Printing Assembly) | 2026-03-09 | 2026-03-14
3.2 | Drive System Code | 2026-03-14 | 2026-03-18
3.3 | Drive System Testing & Navigation | 2026-03-15 | 2026-03-18
4 | Milestone 4
4.1 | Prototype Fabrication ( Sorting System 3D printing) | 2026-03-19 | 2026-03-21
4.2 | Sorting & Pickup System Code | 2026-03-21 | 2026-03-25
4.3 | Sorting & Pickup System Testing | 2026-03-22 | 2026-03-25
4.4 | Color Sensor Threshold Calibration Report | 2026-03-23 | 2026-03-25
5 | Showcase Video
5.1 | Redesign Prototype (Iteration 2) | 2026-03-25 | 2026-03-27
5.2 | System Integration & Final Performance Testing | 2026-03-27 | 2026-03-30
Final Documentaion
| Product Design Report & Project Development File | 2026-04-01 | 2026-04-09